## Cover Page
FRIEND BOOK(SOCIAL MEDIA APPLICATION)
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Shubham Nayak , Punit Mishra , Sonal Agarwal , Harshal Taori , Nilesh Kumar Nayak , Devika Pagare | Akhilesh Kumar Soni
| Role | Software Developer | Technical Trainer
| Signature | Shubham Nayak-2113068 , Punit Mishra-2136594 , Sonal Agrawal-2136967 , Harshal Taori- 2113696, Nilesh Kumar Nayak-2136553 , Devika Pagare-2129822
| Date | 2022-08-01
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog - Instructions C3: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/3.
Sprint 1/2/3
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sample
Sprint Backlog <Contract_Management> Project ID: <INTBGL20ES001/A003> C3: Protected Controlled Copy
USER STORY & TASK ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | Sign up/Register | 1
Task_1 | Register Page Design |  | Ujjal |  | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Develop the code |  | Vikalp |  | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Store the user in User Table |  | Vaibhav |  | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Develop code for Data validation |  | Vishwas |  | 0.5 | 1 | 2 | 3 | 1 | 0
US_2 | Sign in/Log in | 1
Task_1 | Design Sign in Page |  | Trainee_3 |  | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Develop the code for login |  | Trainee_4 |  | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Develop code for redirecting |  | Trainee_3 |  | 2 | 2 | 5 | 0 | 1 | 0
Task_4 | Develop code for zuul gateway |  | Trainee_4 |  | 5 | 5 | 9 | 5 | 1 | 0
US_3 | Uploading content | 5
Task_1 | Create Post Table |  | Trainee_1 |  | 8 | 6 | 0 | 0 | 0 | 0
Task_2 | Design Post Component |  | Trainee_2 |  | 3 | 1 | 3 | 3 | 3 | 0
Task_3 | Store post in Table |  | Trainee_3 |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1
Task_4 | Develop code for posting images |  | Trainee_4 |  | 2 | 0.5 | 0 | 0 | 0 | 0
US_4 | Like/Comment | 2
Task_1 | Design like/comment section |  |  |  | 9 | 4 | 2 | 2 | 1 | 1
Task_2 | Create Like,comment table |  |  |  | 6 | 6 | 3 | 3 | 3 | 1
Task_3 | Develop code for storing like |  |  |  | 6 | 2 | 8 | 8 | 1 | 0
Task_4 | Develop code for storing comments |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
US_5 |  | 3
Task_1 |  |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1
Task_2 |  |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9
Task_3 |  |  |  |  | 9 | 9 | 9 | 4 | 3 | 3
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0
TOTAL |  |  |  |  | 78 | 60 | 59 | 41 | 20 | 18

## Sprint -1
Sprint Backlog <SOCIAL MEDIA APPLICATION> Project ID: <ADMJFS001/POD3> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | User registration | 1 |  | completed
Task_1 | Register Page Design |  | Punit,Harshal |  | 18.5 | 5 | 4 | 4 | 0 | 0
Task_2 | Develop the code |  | Shubham |  | 19 | 4 | 3 | 5 | 4 | 2
Task_3 | Store the user in User Table |  | Nilesh |  | 11.5 | 2 | 2 | 2 | 3 | 2
Task_4 | Develop code for Data validation |  | Sonal,Devika |  | 13 | 1 | 2 | 2 | 3 | 3
US_2 | Sign in/Log in | 1 |  | completed
Task_1 | Design Sign in Page |  | Punit,Harshal |  | 13 | 2 | 4 | 4 | 2 | 2
Task_2 | Develop the code for login |  | Nilesh,Devika |  | 24 | 6 | 4 | 4 | 5 | 4
Task_3 | Develop code for redirecting |  | Shubham |  | 13.5 | 2 | 3.5 | 2 | 2 | 4
Task_4 | Develop code for zuul gateway |  | Sonal |  | 5 | 2 | 1 | 0.5 | 0.5 | 0
US_3 | Uploading content | 5 |  | completed
Task_1 | Create Post Table |  | Devika |  | 18 | 3 | 2 | 1 | 6 | 5
Task_2 | Design Post Component |  | Shubham,Punit |  | 13 | 2 | 2 | 2 | 3 | 4
Task_3 | Store post in Table |  | Harshal |  | 8 | 0.5 | 1 | 3.5 | 1 | 2
Task_4 | Develop code for posting images |  | Sonal,Nilesh |  | 10 | 2 | 2 | 3 | 0.5 | 2
US_4 | Like/Comment | 2 |  | completed
Task_1 | Design like/comment section |  | Sonal,Punit |  | 13 | 3 | 3 | 2 | 2 | 2
Task_2 | Create Like,comment table |  | Harshal |  | 14 | 2 | 3 | 2 | 3 | 3
Task_3 | Develop code for storing like |  | Nilesh,Sonal |  | 12.5 | 3 | 3 | 1.5 | 3 | 2
Task_4 | Develop code for storing comments |  | Devika |  | 9 | 3 | 3 | 2 | 1 | 0
US_5 | Update Profile Details | 2 |  | completed
Task_1 | Design Profile details section |  | Devika,Harshal |  | 18 | 1 | 3 | 3 | 5 | 6
Task_2 | Update Profile Details in Profile table |  | Sonal,Shubham,Nilesh |  | 14 | 2 | 4 | 3 | 4 | 1.5
US_6 | Search User | 2 |  | completed
Task_1 | Design Search Bar |  | Punit |  | 10 | 3 | 2 | 2 | 2 | 1
Task_2 | Develop code for search |  | Punit, Shubham |  | 5 | 2 | 1 | 0.5 | 0.5 | 1
US_7 | Follow Friend | 2 |  | completed
Task_1 | Develop code for follow button |  | Sonal |  | 8 | 3 | 2 | 0.5 | 0 | 2
Task_2 | Develop code for storing followers in Follow table |  | Devika,Nilesh |  | 7 | 2 | 2 | 1 | 1 | 1
US_8 | Navigate to the user profile | 8 |  | completed
Task_1 | Develop code for adding link to the ui |  | Shubham |  | 9 | 2 | 2 | 1 | 2 | 1
Task_2 | Develop code to navigate to the profile |  | Harshal |  | 5 | 0.5 | 0.5 | 1 | 1 | 1
TOTAL |  |  |  |  | 247 | 45.5 | 49.5 | 46.5 | 48 | 44.5

## Sprint -2
Sprint Backlog SOCIAL MEDIA APPLICATION Project ID:POD3 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_9 | Report user | 8 |  | completed
Task_1 | Design code for report button functionality |  | Devika |  | 16 | 5 | 3 | 2 | 1 | 1
Task_2 | Create table for report |  | Punit,Nilesh |  | 14.5 | 3 | 4 | 2 | 2 | 3
Task_3 | Develop code for storing reported posts |  | Sonal,Shubham |  | 12 | 3 | 4 | 2 | 1.5 | 0.5
US_10 | View Profile/HomePage | 2 |  | completed
Task_1 | Design HomePage |  | Sonal, Shubham |  | 12 | 1 | 1.5 | 3 | 4 | 4
Task_2 | Design Profile Page |  | Punit,Devika |  | 15 | 1 | 2 | 4 | 4 | 2
Task_3 | Redirection of Pages |  | Nilesh |  | 10 | 1 | 1 | 2 | 1 | 1.5
US_11 | Send and Recieve Message | 1 |  | completed
Task_1 | Design chatbox |  | Harshal,Shubham |  | 12 | 2 | 3 | 3 | 3 | 1
Task_2 | Develop web socket code |  | Sonal,Devika |  | 16 | 3 | 2 | 2 | 4 | 4
Task_3 | Develop code for stomp client |  | Nilesh,Punit |  | 18 | 3 | 3 | 1 | 5 | 4
US_12 | Recieve Reported Posts | 13 |  | completed
Task_1 | Design Admin App |  | Harshal |  | 15 | 4 | 4 | 2 | 1 | 2
Task_2 | Develop code for showing reported posts |  | Punit |  | 18.5 | 1.5 | 1.5 | 1.5 | 2 | 2
US_13 | Remove the flag from the post | 13 |  | completed
Task_1 | Add Remove button to UI and add functionality |  | Devika |  | 15 | 1 | 4 | 5 | 2 | 2
Task_2 | Develop code for Removing Post from Admin app and Reported Post |  | Sonal |  | 12 | 2 | 1 | 1 | 1 | 2
US_14 | Delete the Post | 13 |  | completed
Task_1 | Add Remove button to UI and add functionality |  | Nilesh |  | 15 | 4 | 2 | 4 | 2 | 2
Task_2 | Develop code for Deleting the reported post and updating in db |  | Shubham |  | 12 | 2 | 1.5 | 4 | 2 | 3
TOTAL |  |  |  |  | 213 | 36.5 | 37.5 | 38.5 | 35.5 | 34

## Data (hidden)
In-Progress
Completed
N/A